## 4th Quater
Consilidated District Anuval Implementation Programme - 2021 4th Quarter physical &Financial Progress Report
Divisional Secretariat:- Valisouth,Uduvil
S.N | Main Sector Code No | Sub Sector Code No | Sector | Description of works | Status put C/N (New work-N/Continuous work-C) | G.N Divison No | D.S Divison | Implementing/Responsibility Agency | Source of fund | Total Estimated Cost (TEC) in Rs ''000'' | Plan for Implementation |  | Allocation for the Year in Rs ''000'' | Financial & Physical Quarterly Financial targets (in Rs.''000'') |  |  |  | Physical |  | No.of Beneficiaries (in Person-P/Families-F) | Project Output
[11 empty] | Date of Commencement | Date of Completion |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr | Unit(eg-km/sq.km/ft/sq.ft/Nos) | Annual Target(in number)
1 | 300 | 340 | 343 | Construction of Disabled Toilet for Disabled person | N | J/196, J/194 | Uduvil | DS office Uduvil | Department Of Social Services | 416000 | 2021-04-15 | 15.Jul | 416000 |  | 416000 |  |  | Nos |  | 2 | SSO
2 | 600 | 620 | 621 | Construction of Access Slope For Disable Person | N | J/185 J/202 J/201 | Uduvil | DS office Uduvil | Department Of Social Services | 200000 | 2021-04-01 | 2021-06-01 | 200000 |  | 200000 |  | 50000 |  |  | 4
3 | 600 | 630 | 632 | Self Employment Assitance to Disable Person | N | J/192 J/199 J/194 j/207 | Uduvil | DS office Uduvil | Department Of Social Services | 300000 | 2021-04-01 | 2021-12-31 | 300000 |  | 300000 |  |  |  |  | 4
4 |  |  |  | Supply of Adjestable bed to Disabled Person | N | J/208,J/202, J/186 | Uduvil | DS office Uduvil | Department Of Social Services | 225000 | 2021-05-10 | 2021-08-10 | 225000 |  | 225000 |  |  |  |  | 3
5 | 600 | 630 | 632 | Providind PAMA&Disease Payment ForVulnurable Families | N | All Division | Uduvil | DS office Uduvil | Department Of Social Services |  | 2021-01-01 | 2021-12-31 | 909100 |  |  | 4074800 | 3906350 |  |  | 1951
6 | 600 | 630 | 632 | providing Elders Payment For Over 70 elders | N | All Division | Uduvil | DS office Uduvil | Elders Secretariat |  | 2021-01-01 | 2021-12-31 | 35376000 |  |  | 880800 | 8360000 |  |  | 1474
7 | 600 | 630 | 632 | Providing Disable Payment for Disable | N | All Division | Uduvil | DS office Uduvil | NSPD |  | 2021-01-01 | 2021-12-31 | 21600000 |  |  | 5385000 | 5355000 |  |  | 360
8 | 600 | 630 | 632 | Providing Kidney Payment for Kidny Person | N | All Division | Uduvil | DS office Uduvil | NSPD |  | 2021-01-01 | 2021-12-31 | 1740000 |  |  | 1305000 | 435000 |  |  | 29
9 | 700 | 710 | 711 | Improvement Building Structiure fitting permanant Cubbord | N | DS office Uduvil | Uduvil | DS office Uduvil | Ministry of Public Administration | 130000 | 15.01.2021 | 23.04.2021 | 130000 |  | 130000 | - |  |  |  | - | Acct
10 | 700 | 710 | 712 | providing Machinary Equipment for extenison of intercom | C | DS office Uduvil | Uduvil | DS office Uduvil |  | 160000 | 01.02.2021 | 21.04.2021 | 160000 | 119000 | 17000 | 16450 | 73510 |  |  | -
11 | 700 | 720 | 722 | providing Furniture office equipment foroffice development | N | DS office Uduvil | Uduvil | DS office Uduvil |  | 600000 | 01.03.2021 | 31.12.2021 | 600000 | 200200 | 230377.5 | 159000 | 9607.5 |  |  | -
12 | 700 | 720 | 721 | Improvement cycle shed floor concrete work | C | DS office Uduvil | Uduvil | DS office Uduvil |  | 75000 | 22.02.2021 | 23.07.2021 | 75000 |  |  | 58048 |  |  |  | -
13 | 700 | 710 | 712 | Maintenance front Premisesarea of ds office | C | DS office Uduvil | Uduvil | DS office Uduvil |  | 650000 | 22.03.2021 | 31.12.2021 | 650000 |  |  | 174894 | 72365.94 |  |  | -
14 | 700 | 720 | 723 | Maintenance of wiring work | C | DS office Uduvil | Uduvil | DS office Uduvil |  | 100000 | 19.02.2021 | 29.03.2021 | 100000 |  | 100000 |  |  |  |  | -
15 | 600 | 630 | 633 | Supply of Construction Materials for Ambuliyappulam Gnanavairavar Temple | N | J/183 | Uduvil | DS office Uduvil | Ministry of Finance | 180000 | 01.06.2021 | 30.09.2021 | 180000 |  |  | - | 179100 | Nos |  | 50
16 | 600 | 610 | 612 | Supply of Furniture for Uthajasoorijan Preschool Management Committee | N | J/185 | Uduvil | DS office Uduvil | Ministry of Finance | 50000 | 01.06.2021 | 30.09.2021 | 50000 |  |  | - | 49750 | Nos |  | 100
17 | 600 | 610 | 612 | Supply of Sound System for Sir Pararaja Sekara Pillaiyar araanari School | N | J/188 | Uduvil | DS office Uduvil | Ministry of Finance | 70000 | 01.06.2021 | 30.09.2021 | 70000 |  |  | 56800 | 12850 | Nos |  | 100
18 | 350 |  | 353 | Supply of Furnitures for Thavady North woman RDS | N | J/194 | Uduvil | DS office Uduvil | Ministry of Finance | 60000 | 01.06.2021 | 30.09.2021 | 60000 |  |  | - | 59700 | Nos |  | 100
19 | 600 | 610 | 612 | Supply of Photo Copier for J/Mylany Saiva Maha Vidyalayam | N | J/195 | Uduvil | ZED, Valikamam | Ministry of Finance | 120000 | 01.06.2021 | 30.09.2021 | 120000 |  |  | - | 119400 | Nos |  | 500
20 | 600 | 630 | 634 | Supply of Sports Equipments for Iyanar Youth club | N | J/198 | Uduvil | DS, Uduvil | Ministry of Finance | 40000 | 01.06.2021 | 30.09.2021 | 40000 |  |  | 27050 | 12750 | Nos |  | 50
21 | 600 | 630 | 634 | Construction of a Movable Steps for J/Skandabarodaya College | N | J/200 | Uduvil | ZED, Valikamam | Ministry of Finance | 100000 | 01.06.2021 | 30.09.2021 | 100000 |  |  | - | 98000 | Sq.ft |  | 1500
22 | 600 | 630 | 633 | Renovation of Building for Sri Muthumary Ambal Alayam | N | J/203 | Uduvil | DS, Uduvil | Ministry of Finance | 130000 | 01.06.2021 | 30.09.2021 | 130000 |  |  | - | 127400 | Sq.ft |  | 200
23 | 600 | 630 | 633 | Supply of Construction Materials for Gnana Vairavar Temple | N | J/203 | Uduvil | DS, Uduvil | Ministry of Finance | 150000 | 01.06.2021 | 30.09.2021 | 150000 |  |  | - | 149250 | Nos |  | 150
24 | 600 | 620 | 621 | Renovation of Water Tank for Earlalai south A.M.T.M School | N | J/203 | Uduvil | ZED, Valikamam | Ministry of Finance | 75000 | 01.06.2021 | 30.09.2021 | 75000 |  |  | - | 73500 | Sq.ft |  | 250
25 | 600 | 630 | 634 | Renovation of Playground for Five Star Sports Club | N | J/204 | Uduvil | DS, Uduvil | Ministry of Finance | 130000 | 01.06.2021 | 30.09.2021 | 130000 |  |  | - | 127400 | Sq.ft |  | 80
26 | 600 | 610 | 611 | Renovation of Class Room for J/Earlalai Maha Vidyalayam | N | J/206 | Uduvil | ZED, Valikamam | Ministry of Finance | 200900 | 01.06.2021 | 30.09.2021 | 200900 |  |  | - | 199875 | Sq.ft |  | 300
27 | 600 | 630 | 634 | Supply of Sports Equipments for Kuppilan South Kurinchi Kumaran Sports Club | N | J/210 | Uduvil | DS, Uduvil | Ministry of Finance | 30000 | 01.06.2021 | 30.09.2021 | 30000 |  |  | 29700 | 150 | Nos |  | 75
28 | 600 | 630 | 634 | Supply of Sports Equipments for Skanda star sports club | N | J/200 | Uduvil | DS, Uduvil | Ministry of Finance | 50000 | 01.06.2021 | 30.09.2021 | 50000 |  |  | 49500 | 250 | Nos |  | 70
29 | 600 | 630 | 633 | Reconstruction of the Building for Inuvil Kanthaswamy Kovil Ilanthodar Sabai | N | J/188 | Uduvil | DS, Uduvil | Ministry of Finance | 50000 | 01.06.2021 | 30.09.2021 | 50000 |  |  | - | 49000 | Sq.ft |  | 100
30 | 600 | 630 | 634 | Supply of Sports Equipments for Lambothara Sports Club | N | J/188 | Uduvil | DS, Uduvil | Ministry of Finance | 20000 | 01.06.2021 | 30.09.2021 | 20000 |  |  | 17650 | 2250 | Nos |  | 80
31 | 600 | 630 | 634 | Supply of Sports Equipments for Inuvil Kalaioli Mantram Sports Club | N | J/191 | Uduvil | DS, Uduvil | Ministry of Finance | 20000 | 01.06.2021 | 30.09.2021 | 20000 |  |  | 19800 | 100 | Nos |  | 85
32 | 600 | 630 | 634 | Supply of Sports Equipments for Suthumalai Sripuvaneswari Ambal Sports Club | N | J/194 | Uduvil | DS, Uduvil | Ministry of Finance | 20000 | 01.06.2021 | 30.09.2021 | 20000 |  |  | 19800 | 100 | Nos |  | 70
33 | 600 | 630 | 634 | Supply of Sports Equipments for ArignarI Aiyanna Sports Club | N | J/199 | Uduvil | DS, Uduvil | Ministry of Finance | 15000 | 01.06.2021 | 30.09.2021 | 15000 |  |  | 14850 | 75 | Nos |  | 50
34 | 600 | 630 | 634 | Supply of Sports Equipments for Skanda Stars Sports Club | N | J/200 | Uduvil | DS, Uduvil | Ministry of Finance | 20000 | 01.06.2021 | 30.09.2021 | 20000 |  |  | - | 19900 | Nos |  | 70
35 | 600 | 630 | 634 | Construction of Security Wall for J/Earlalai Maha Vid | N | J/206 | Uduvil | ZED, Valikamam | Ministry of Finance | 290000 | 01.06.2021 | 30.09.2021 | 290000 |  |  | - | 284200 | Sq.ft |  | 750
36 | 600 | 630 | 634 | Supply of Furniture and Equipments for Sri Penni Blessing Church | N | J/187 | Uduvil | DS, Uduvil | Ministry of Finance | 25000 | 10.10.2021 | 31.12.2021 | 25000 |  |  |  | 24875 | Nos |  | 120
37 | 600 | 630 | 634 | Supply of Furniture and Equipments for Sri Vageeswary Drama Union | N | J/203 | Uduvil | DS, Uduvil | Ministry of Finance | 25000 | 10.10.2021 | 31.12.2021 | 25000 |  |  |  | 24875 | Nos |  | 40
38 | 600 | 630 | 634 | Supply of Sports Equipments for Sri Murugan United Sports Cub | N | J/202 | Uduvil | DS, Uduvil | Ministry of Finance | 50000 | 10.10.2021 | 31.12.2021 | 50000 |  |  |  | 49750 | Nos |  | 45
39 | 600 | 630 | 634 | Supply of Sports Equipments Fof Real Stars Youth Club | N | J/199 | Uduvil | DS, Uduvil | Ministry of Finance | 25000 | 10.10.2021 | 31.12.2021 | 25000 |  |  |  | 24875 | Nos |  | 50
40 | 600 | 630 | 634 | Supply of Sports Equipments for Kalajothy Sports Club | N | J/190 | Uduvil | DS, Uduvil | Ministry of Finance | 25000 | 10.10.2021 | 31.12.2021 | 25000 |  |  |  | 24875 | Nos |  | 50
41 | 600 | 630 | 634 | Supply of Sound Equipments for Sri Sri Radha Krishna Temple | N | J/186 | Uduvil | DS, Uduvil | Ministry of Finance | 50000 | 10.10.2021 | 31.12.2021 | 50000 |  |  |  | 49750 | Nos |  | 250
42 | 600 | 630 | 634 | Renovation of Athi Vairavar Annamar Nagathampiran Alayam | N | J/209 | Uduvil | DS, Uduvil | Ministry of Finance | 245000 | 10.10.2021 | 31.12.2021 | 245000 |  |  |  | 242500 | Sq.ft |  | 150
43 | 600 | 630 | 634 | Supply of Sports Equipments and Uniforms Thachchi Sports Associaton | N | J/183 | Uduvil | DS, Uduvil | Ministry of Finance | 50000 | 10.10.2021 | 31.12.2021 | 5000 |  |  |  | 49750 | Nos |  | 75
44 | 600 | 630 | 634 | Supply of Projector, Screen and Sound System for Vakeesvari Drama Society | N | J/203 | Uduvil | DS, Uduvil | Ministry of Finance | 150000 | 10.10.2021 | 31.12.2021 | 150000 |  |  |  | 149250 | Nos |  | 40
45 | 600 | 630 | 634 | Renovation for Ambuliyappulam Gnavairavar Temple | N | J/183 | Uduvil | DS, Uduvil | Ministry of Finance | 79200 | 10.10.2021 | 31.12.2021 | 79200 |  |  |  | 78400 | Sq.ft |  | 150
46 | 600 | 630 | 634 | Supply of Sports Equipment for Sivan Sports club at Chunnkam | N | J/196 | Uduvil | DS, Uduvil | Ministry of Finance | 60000 | 10.10.2021 | 31.12.2021 | 60000 |  |  |  | 59700 | Nos |  | 80
47 | 600 | 630 | 634 | Supply of Sports Equipments for Kandarodai People's development youth club | N | J/200 | Uduvil | DS, Uduvil | Ministry of Finance | 60000 | 10.10.2021 | 31.12.2021 | 60000 |  |  |  | 59700 | Nos |  | 65
48 | 600 | 630 | 634 | Supply of Securety box and Furniture Earlali south Sri Vinaykar ikkiya nanaya sankam | N | J/202 | Uduvil | DS, Uduvil | Ministry of Finance | 40000 | 10.10.2021 | 31.12.2021 | 40000 |  |  |  | 39800 | Nos |  | 75
49 | 600 | 630 | 634 | Supply of water facilities for Saiva Valipar pre school | N | J/202 | Uduvil | DS, Uduvil | Ministry of Finance | 70000 | 10.10.2021 | 31.12.2021 | 70000 |  |  |  | 69600 | Nos |  | 30
50 | 600 | 630 | 634 | Supply of Sports Equipments for Gnanamurugan Sports Club at Mylankadu | N | J/203 | Uduvil | DS, Uduvil | Ministry of Finance | 50000 | 10.10.2021 | 31.12.2021 | 50000 |  |  |  | 49750 | Nos |  | 125
51 | 600 | 630 | 634 | Construction of Electricity Facilities for Earlalaii Usathi odai hindu mayanam | N | J/201 | Uduvil | DS, Uduvil | Ministry of Finance | 196980 | 10.10.2021 | 31.12.2021 | 196980 |  |  |  | 195975 | Sq.ft |  | 1000
52 | 600 | 630 | 634 | Supply of Multimedia projector & Smart board for Iyanar Community Centre | N | J/198 | Uduvil | DS, Uduvil | Ministry of Finance | 100000 | 10.10.2021 | 31.12.2021 | 100000 |  |  |  | 99500 | Nos |  | 500
53 | 600 | 630 | 634 | Supply of Smart Class room Equipments. For Divya Preschool - Earlalai | N | J/204 | Uduvil | DS, Uduvil | Ministry of Finance | 100000 | 10.10.2021 | 31.12.2021 | 100000 |  |  |  | 99500 | Nos |  | 200
54 | 600 | 630 | 634 | Supply of Sports Equipments for Erlalai Young Mens Hindu Association | N | J/206 | Uduvil | DS, Uduvil | Ministry of Finance | 20000 | 10.10.2021 | 31.12.2021 | 20000 |  |  |  | 19900 | Nos |  | 350
55 | 600 | 630 | 634 | Supply of Sports Equipments for Hindu Sports Club | N | J/189 | Uduvil | DS, Uduvil | Ministry of Finance | 20000 | 10.10.2021 | 31.12.2021 | 20000 |  |  |  | 19900 | Nos |  | 150
56 | 600 | 630 | 634 | Construction of Water & Sanitory facilities for Jonians Pre School | N | J/203 | Uduvil | DS, Uduvil | Ministry of Finance | 132300 | 10.10.2021 | 31.12.2021 | 132300 |  |  |  | 130950 | Sq.ft |  | 100
57 | 600 | 630 | 634 | Construction of Safety fence items for Oli Nila Sports Club | N | J/208 | Uduvil | DS, Uduvil | Ministry of Finance | 201880 | 10.10.2021 | 31.12.2021 | 201880 |  |  |  | 199820 | Sq.ft |  | 350
58 | 600 | 630 | 634 | Supply of Sports Equipemtns for Gnanakala Sports Club | N | J/210 | Uduvil | DS, Uduvil | Ministry of Finance | 2950 | 10.10.2021 | 31.12.2021 | 29850 |  |  |  | 29700 | Nos |  | 250
59 | 600 | 630 | 634 | Construction of Safety fence items for Kali Ambal Sports Club | N | J/192 | Uduvil | DS, Uduvil | Ministry of Finance | 201880 | 10.10.2021 | 31.12.2021 | 201880 |  |  |  | 199820 | Sq.ft |  | 400
60 | 600 | 630 | 634 | Supply of Sports Equipments for Aarivoli Sports Club | N | J/210 | Uduvil | DS, Uduvil | Ministry of Finance | 29850 | 10.10.2021 | 31.12.2021 | 29850 |  |  |  | 29700 | Nos |  | 150
61 | 600 | 630 | 634 | Supply of Sports Equipments for Ganamurugan Sports Club | N | J/203 | Uduvil | DS, Uduvil | Ministry of Finance | 27860 | 10.10.2021 | 31.12.2021 | 27860 |  |  |  | 27720 | Nos |  | 200
62 | 600 | 630 | 634 | Renovation for Mahakali Ambal Temple | N | J/198 | Uduvil | DS, Uduvil | Ministry of Finance | 49000 | 10.10.2021 | 31.12.2021 | 48500 |  |  |  | 48500 | Sq.ft |  | 300
63 | 600 | 620 | 624 | Providing Medical Assistance Payment childrens | N | All Division | Uduvil | DS, Uduvil | Department of probation and Child care services |  | 24.11.2021 | 24.11.2021 | 15000 | 15000 |  | - |  | Nos |  | 18 | CRPO
64 | 600 | 630 | 634 | Providing Schoo bag payment students | N | All Division |  | DS, Uduvil | Department of probation and Child care services |  | 22.03.2021 | 22.03.2021 | 6000 | 6000 |  | - |  | Nos |  | 30
65 | 600 | 630 | 631 | providing Allowance for twin Children | N | All Division | Uduvil | DS, Uduvil | Department of probation and Child care services |  | 27.04.2021 | 27.04.2021 | 15000 |  | 7500 | - | 7500 | Nos |  | 75
66 | 600 | 630 | 632 | Self Employment maintence Project | N | All Division | Uduvil | DS, Uduvil | Department of probation and Child care services |  | 07.05.2021 | 30.11.2021 | 90000 |  | 60000 | - | 30000 | Nos |  | 60
67 | 600 | 630 | 631 | Kapakaru Deeguru | N | All Division | Uduvil | DS, Uduvil | Department of probation and Child care services |  | 07.05.2021 | 30.11.2021 | 56000 |  | 33600 | - | 22400 | Nos |  | 70
68 | 600 | 630 | 634 | Infrastructure Improvement program for Rural Playgrounds | c | J/210 | Uduvil | DS office Uduvil | State Ministry of Rural and School Sports Infrastucture Improvement | 15000000 | 05.03.2021 | 23.08.2021 | 15000000 |  | 701475 | 791025 |  | Nos |  | 50
69 | 600 | 630 | 632 | Welfare centre Maintenance | N | J/196,J/199,J/187,J/200 | Uduvil | DS office Uduvil | State Ministry of Rural Housing and Construction & Building Materials Industries Promotion |  | 01.01.2021 | 31.12.2021 | 621000 | 104694.8 | 78756 | 55368 | 230837.55 |  |  | 131
70 | 600 | 630 | 632 | Saubhayga Production Village Programme | N | All Division | Uduvil | DS office Uduvil | State Ministry of Samurdhi, House hold Economic, Micro finance, Self Employment and Business Development Battaramula |  | 12.02.2021 | 31.12.2021 | 7277064.38 |  |  | 24875 | 720606.63
71 | 600 | 630 | 633 | Mylankadu Union of Cultural Development Centre | N | J/203, | Uduvil | DS office Uduvil | National Disaster Relief Service Centre |  | 05.04.2021 | 09.07.2021 | 980000 |  | 450000 |  |  | Nos |  | 100
72 | 600 | 630 | 632 | Renovation of partly House |  | J/182,J/185J/187 J/188 J/192 J/193 J/196 J/199 J/200J/203 J/205J/208 | Uduvil | DS office Uduvil | National Disaster Relief Service Centre |  | 15.01.2021 | 08.03.2021 | 293845.18 |  | 293845.18 |  |  | Nos |  | 20
73 | 600 | 630 | 632 | Construction of onion Shed farmers | N | All Division | Uduvil | DS office Uduvil | Ministry of Agriculture |  | 05.07.2021 | 31.08.2021 | 4455000 |  |  | 472500 | 3982500 | Nos |  | 66
74 | 600 | 630 | 631 | Children's Day | N | All Division | Uduvil | DS office Uduvil | National Chilld Protection Authority |  | 06.10.2021 | 06.10.2021 | 13800 |  |  | 13800 |  | Nos |  | 50
75 | 600 | 630 | 631 | House (0.6M) | N | All Division | Uduvil | DS office Uduvil | State Ministry of Rural Housing and Construction & Building Materials Industries Promotion | 30447000 | 30.09.2021 | 31.12.2021 | 15050000 |  |  |  | 15397000 | Nos |  | 43F
76 | 600 | 630 | 631 | House (1M) | N | All Division | Uduvil | DS office Uduvil | State Ministry of Rural Housing and Construction & Building Materials Industries Promotion | 99500000 | 30.09.2021 | 31.12.2021 | 39200000 |  |  | 3000000 | 57300000 | Nos |  | 98F
77 | 600 | 630 | 632 | Program of Creat one rural industrial entrepreneur fro grama nilathari division | N | All Division | Uduvil | DS office Uduvil | State Ministry of rattan brass pottery furniture and industry promotion | 2020728.29 | 16.04.2021 | 31.12.2021 | 2020728.29 |  |  |  | 2020583.94 | Nos |  | 28
78 | 600 | 630 | 632 | Human Trafficking and safe lobour migration | N | All Division | Uduvil | DS office Uduvil | Ministry of foreign Employment |  | 29.11.2021 | 29.11.2021 | 10000 |  |  |  | 10000 | Nos |  | 30
79 | 600 | 630 | 633 | Housing damage | N | J/185,J/188,J/191,J/190,J/200,J/209 | Uduvil | DS office Uduvil | National Disaster Relief Service Centre | 87943.6 | 09.08.2021 | 31.12.2021 | 87943.6 |  |  |  | 47943.6 | Sq.ft
80 | 600 | 630 | 633 | Housing damage | N | All Division | Uduvil | DS office Uduvil | National Disaster Relief Service Centre | 94093.5 | 08.07.2021 | 31.12.2021 | 94093.5 |  |  |  | 94093.5 | Sq.ft |  | 5
81 | 600 | 630 | 631 | Meeting Volunteer | N | All Division | Uduvil | DS office Uduvil | Child Probation and child care services |  | 30.10.2021 | 30.10.2021 | 5000 |  |  |  | 5000 | Nos |  | 20
82 | 600 | 630 | 631 | Stationary Issued Children club | N | All Division | Uduvil | DS office Uduvil |  |  | 30.10.2021 | 30.10.2021 | 2500 |  |  |  | 2500 | Nos |  | 10
83 | 600 | 630 | 631 | Divisional Monitoring Programme | N | All Division | Uduvil | DS office Uduvil |  |  | 30.12.2021 | 30.12.2021 | 2000 |  |  |  | 2000 | Nos |  | 10
84 | 600 | 630 | 631 | Program Internet Safety | N | All Division | Uduvil | DS office Uduvil |  |  | 30.12.2021 | 30.12.2021 | 5000 |  |  |  | 5000 | Nos |  | 20
85 | 600 | 630 | 632 | Disable Programme | N | All Division | Uduvil | DS office Uduvil | DOME |  | 09.11.2021 | 09.11.2021 | 25000 |  |  |  | 25000 | Nos |  | 50
86 | 600 | 630 | 632 | Parents Programme | N | All Division | Uduvil | DS office Uduvil |  |  | 18.03.2021 | 18.03.2021 | 2500 |  |  |  | 2500 | Nos |  | 10
87 | 600 | 630 | 632 | Self Employment Programme | N | All Division | Uduvil | DS office Uduvil |  |  | 17.03.2021 | 17.03.2021 | 2500 |  |  |  | 2500 | Nos |  | 10
88 | 600 | 630 |  | Provided School Kids | N | J/184 | Uduvil | DS office Uduvil |  |  | 09.12.2021 | 09.12.2021 | 30350 |  |  |  | 30350 | Nos |  | 25
89 | 600 | 630 | 632 | Saubhayga Production Village Programme Stage 2 | N | J/191 | Uduvil | DS office Uduvil | State Ministry of Samurdhi, House hold Economic, Micro finance, Self Employment and Business Development Battaramula | 3000000 | 14.10.2021 | 31.12.2021 | 3000000 |  |  |  | 2970000 | Nos |  | 150
90 | 600 | 630 | 633 | Our teachers covid - 19 Payment | N | Chankanai, Thellipalai,Uduvil | Uduvil | DS office Uduvil | Department Hindu Cultural Affairs |  | 12.12.2021 | 12.12.2021 | 10000 |  |  |  | 10000 | Nos |  | 150
91 | 600 | 630 | 632 | sanition Stage 1 | N | All Division | Uduvil | DS office Uduvil | State Ministry of Rural and Constouction & Bulding Meterial Industries Promotion | 3244000 | 17.12.2021 | 31.12.2021 |  |  |  |  | 2000000 | Nos |  | 88
92 | 600 | 630 | 632 | 200000 Families Empowerment Programme 2021 | N | All Division | Uduvil | DS office Uduvil | Samurdhi |  | 15.01.2021 | 31.12.2021 | 22427410.3 |  |  |  | 11676775.9 | Nos |  | 450
93 | 600 | 630 | 632 | Surakimugaganga | N | J/197 | Uduvil | DS office Uduvil | Ministry of Environment |  | 10.11.2021 | 20.12.2021 | 6000 |  |  |  | 6000
94 | 600 | 630 | 632 | Green house | N | J/197 | Uduvil | DS office Uduvil |  |  | 29.12.2021 | 31.12.2021 | 15000 |  |  |  | 15000